## SAP Document Export
Related Simplification Items | Activities | Phase | Condition | Additional Information
ABAPTWL - Cleanup of orphaned objects (SI02: AS_ABAP_CLEANUP) | Custom Code Adaption | Before or during conversion project | Mandatory | Remove usage of obsolete SAP objects from custom code.
ABAPTWL - Dual Stack not supported (SI06: AS_ABAP_DUAL_STACK) | Landscape Redesign | Before conversion project | Mandatory | Split your dual stack system into separate ABAP and Java instances.
ABAPTWL - SSCR license key procedure is no longer supported (SI03: AS_ABAP_SSCR) | Process Design / Blueprint | Before or during conversion project | Optional | Setup control of development activities as recommended in SAP note 2309060 .
ABAPTWL - SSCR license key procedure is no longer supported (SI03: AS_ABAP_SSCR) | User Training | Before or during conversion project | Optional | Educate developers about process changes on controlling development activities.
ABAPTWL - VM Container not supported (SI04: AS_ABAP_VMCONTAINER) | Custom Code Adaption | Before or during conversion project | Mandatory | Remove any VMC usage in your custom applications.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Business Decision | Before conversion project | Mandatory | Decide about future ledger approach for asset accounting.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Business Operations | During conversion project | Mandatory | Execute year-end and month-end closing activities.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Custom Code Adaption | During conversion project | Mandatory | For required custom code adaption refer to simplification item SI1: FIN_AA and SAP note 2270387.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Customizing / Configuration | During conversion project | Mandatory | Perform customizing and configuration required for preparing the data migration and for the future asset accounting design in SAP S/4HANA.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data cleanup / archiving | Before conversion project | Optional | Reduce number of asset accounting documents to avoid unnecessary data error corrections and to minimize conversion downtime.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data correction | Before or during conversion project | Mandatory | Check and correct inconsistent data which is relevant for the conversion.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data migration | During conversion project | Mandatory | Perform data migration to new SAP S/4HANA data model.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Interface Adaption | During conversion project | Mandatory | Adapt or replace obsolete or changed legacy data transfer methods.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Process Design / Blueprint | Before or during conversion project | Mandatory | Create blueprint for required Asset Accounting configuration in SAP S/4HANA.
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | User Training | During conversion project | Mandatory | Inform users about changes in Asset Accounting.
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Software Upgrade / Maintenance | During conversion project | Conditional | Implementation of SAP Notes might be required in case new functionality should not be used
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Software Upgrade / Maintenance | During conversion project | Conditional | Implementation of SAP Notes might be required in case new functionality should be used
S4TWL - Authorization Concept for Supplier Invoice (SI14: PROC_MM_IV_AUTH) | Customizing / Configuration | During conversion project | Mandatory | Users working with supplier invoices, additionally need the authorizations based on M_RECH_BUK
S4TWL - BI Extractors in SAP S/4HANA (SI18: CT_BW_EXTRACTORS) | Interface Adaption | During conversion project | Mandatory | Adjust or change BI extractors.
S4TWL - BI Extractors in SAP S/4HANA (SI18: CT_BW_EXTRACTORS) | New developments | During conversion project | Optional | Develope solutions for obsolete BW extractors
S4TWL - BW Extractors for Dangerous Goods Management and Specification Managemen (SI8: Logistics_PSS) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - BW Extractors for Dangerous Goods Management and Specification Managemen (SI8: Logistics_PSS) | Process Design / Blueprint | Before or during conversion project | Mandatory | The relevant BW extractors and data sources for Dangerous Goods Management and Specification Management are not available within SAP S/4HANA
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | Custom Code Adaption | Before or during conversion project | Conditional | Adjust your custom code according to the new process.
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | Process Design / Blueprint | Before conversion project | Mandatory | Batch Input to maintain customer master and supplier master data is not supported since SAP S/4 HANA 1809, please use one of the following alternatives: Business Partner SOAP Services. Refer to SAP Note 2472030 for more information IDocs (CREMAS/DEBMAS) Mass Transactions (XK99/XD99)
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | User Training | Before or during conversion project | Mandatory
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Business Decision | Before conversion project | Mandatory
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Custom Code Adaption | During conversion project | Conditional | Apply code changes for S/4HANA to reactive NAST based output control
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Customizing / Configuration | During conversion project | Conditional | Define output types or assign channels.
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Process Design / Blueprint | During or after conversion project | Optional | In SAP S/4HANA, a new output management approach has been implemented and is set as the default for newly created billing documents.
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Business Decision | Before conversion project | Mandatory | Before the conversion project you need to make a decision on whether the Business Partner ID and the Customer/Vendor ID should be the same
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Custom Code Adaption | During conversion project | Mandatory | Adapt your Custom Code as per Note 2265093 "Custom Code Adaption" section
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Customizing / Configuration | During conversion project | Mandatory | Start the conversion as per BP_Conversion Document.pdf attached to SAP Note 2211312 Note: If the runtime error "Inconsistency in the dictionary for structure "ZT005_GEN" occurs during the SUM execution, execute the process again.
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Customizing / Configuration | During conversion project | Mandatory | Check CVI customizing and trigger necessary changes e.g. missing BP Role Category, Define Number Assignments according to the S/4 Conversion guide chapter Introduce Business Partner Approach (Customer Vendor Integration) (Note 2265093) Check and maintain BP customizing e.g. missing tax types.
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Mandatory | Implement SAP S/4HANA Conversion Pre-Checks according to the SAP S/4HANA Conversion guide chapter Pre-Checks as per Note 2265093
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Conditional | If the Business Function CA_BP_SO is present in your system -> activate it as per Note 2265093 In case that the Business Function CA_BP_SOA does not yet exist in the system -> you have to create a new Business Function in the customer namespace with the switches VENDOR_SFWS_SC1 and VENDOR_SFWS_SC2. The new customer specific Business Function must be of type Enterprise Business Function (G) - see also Mandatory checks for customer, vendor and contact as per Note 2265093
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Mandatory | Carry out post-implementation steps as per BP_Conversion Document.pdf attached to SAP Note 2211312 The customer/vendor transformation is bidirectional. You can both process customer/vendor master records from business partner maintenance as well as populate data from customer/vendor processing to the business partner. After the successful S/4 conversion process you have to activate the post processing for direction Business Partner a Customer /Vendor.
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Mandatory | Run Business Partner Pre-Check PRECHECK_UPGRADATION_REPORT to verify the results according to the Note 2211312
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Mandatory | Check master data consistency using CVI_MIGRATION_PRECHK and maintain consistency. Check and clean-up customer/vendor data e.g. missing @-sign in the e-mail address.
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data migration | During conversion project | Conditional | Valid for Retail Sites: Customers and vendors assigned to Retail sites are not handled by CVI synchronization (MDS_LOAD_COCKPIT) on SAP ERP 6.0, but by a specific migration process during SAP S/4HANA conversion. See SAP Note 2310884 for more information
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data migration | During conversion project | Conditional | Valid for IS-OIL: In S4HANA all the IS-OIL specific fields (including customer BDRP data fields) have been adapted as per the new Framework of BP. The IS-OIL Fields related to Vendor and Customer now have been moved to BP under the roles FLCU01 (Customer), FLVN01 (Vendor)
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data migration | During conversion project | Mandatory | Perform Synchronization (Data load) via Synchronization Cockpit (Note 2265093)
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Process Design / Blueprint | Before conversion project | Mandatory | There is a list of transactions that redirect you to the transaction BP, as well as a list of obsolete transactions as per Note 2265093 , adjust your business process accordingly
S4TWL - Business Partner Approach (SI2: MasterData_BP) | User Training | During conversion project | Optional | User training to use new transactions for Business Partners in S/4HANA
S4TWL - Business User Management (SI21: BUSINESS_USER) | Customizing / Configuration | During conversion project | Mandatory | Configure update channel for workplace address data If HR integration is active, configure and maintain employee master data
S4TWL - Business User Management (SI21: BUSINESS_USER) | Data correction | Before or during conversion project | Mandatory | check user data (as part of general business partner introduction)
S4TWL - Business User Management (SI21: BUSINESS_USER) | Data migration | During conversion project | Mandatory | If HR integration is active, run HCM business partner synchronization as described in HCM simplification SAP Note 2340095 If HR integration is not active, create or upload person data wiht Fiori app "Maintain employee"
S4TWL - Business User Management (SI21: BUSINESS_USER) | Fiori Implementation | During conversion project | Conditional | If HR integration is not active, implement Fiori app "Maintain employee"
S4TWL - Business User Management (SI21: BUSINESS_USER) | User Training | During conversion project | Mandatory
S4TWL - Changed Interfaces (SI15: CT_Integration) | Interface Adaption | During conversion project | Mandatory | Adjust any interfaces that use obsolete RFC.
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | Custom Code Adaption | During conversion project | Mandatory | Replace custom code refering to old BAPIs
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | Customizing / Configuration | During conversion project | Optional
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | User Training | During conversion project | Optional
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Business Operations | During conversion project | Conditional | If Material ledger is already active => complete step "Post closing" for all ML costing runs created before conversion/upgrade
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Customizing / Configuration | During conversion project | Conditional | If actual costing is active => customize account determination as of SAP S/4HANA 1610
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data cleanup / archiving | Before conversion project | Optional | Archiving historic data
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data correction | During conversion project | Mandatory
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data migration | During conversion project | Mandatory
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Software Upgrade / Maintenance | During conversion project | Mandatory | Implementation of SAP Notes mentioned in SAP Note "2345739" for your corresponding Support Package.
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Business Decision | Before conversion project | Optional
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Process Design / Blueprint | During conversion project | Optional
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | User Training | During conversion project | Mandatory
S4TWL - Custom Fields (SI13: CT_Custom-Fields) | Custom Code Adaption | During or after conversion project | Optional | Enable existing CDS extensions to SAP S/4HANA tables for SAP Fiori applications (raised by ATC checks)
S4TWL - Custom Fields (SI13: CT_Custom-Fields) | Customizing / Configuration | During or after conversion project | Optional | Preapre and enable Custom Database Fields Usage in SAP Fiori Applications
S4TWL - DATA MODEL CHANGES IN FIN (SI1_FIN_General) | Custom Code Adaption | During conversion project | Mandatory | Adapt access to the new simplified Finance data model in your customer-specific programs
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT (MM-IM) (SI1: Logistics_MM-IM) | Business Decision | Before conversion project | Optional | Decide which locking methods to be used for goods movements
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT (MM-IM) (SI1: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT (MM-IM) (SI1: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT (MM-IM) (SI1: Logistics_MM-IM) | Customizing / Configuration | During or after conversion project | Mandatory
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT (MM-IM) (SI1: Logistics_MM-IM) | Technical System Configuration | During conversion project | Optional
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Data migration | After conversion project | Mandatory
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Technical System Configuration | During conversion project | Conditional | If pricing table KONV has been enhanced with customer-specific fields, you must ensure that the appended fields are also added to the new structure PRCS_ELEMENTS_DATA.
S4TWL - Determination of default values in Intrastat reporting (SI3: FIN_SLL_ISR_DV) | Customizing / Configuration | After conversion project | Mandatory
S4TWL - Determination of default values in Intrastat reporting (SI3: FIN_SLL_ISR_DV) | Data correction | After conversion project | Mandatory
S4TWL - Enterprise Search in SAP Product Lifecycle Management (SAP PLM) (SI1: Logistics_PLM) | Custom Code Adaption | During conversion project | Mandatory | Custom code needs to be adjusted to reference to the new model names
S4TWL - Enterprise Search in SAP Product Lifecycle Management (SAP PLM) (SI1: Logistics_PLM) | Customizing / Configuration | During conversion project | Mandatory | With SAP S/4HANA the Enterprise Search models are now replication free search models (using HANA DB tables instead) within SAP Product Lifecycle Management (SAP PLM). The Enterprise Search models' names have changed and due to this， the related customizing (Define Settings for PLM Search under PLM Search) needs to be adjusted. SAP Note 2212593
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | Custom Code Adaption | During conversion project | Conditional | if Fiori has been enhanced SAP ERP 6.0, analyze and perform required enhancements in SAP S/4HANA
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | Fiori Implementation | During conversion project | Conditional | if Fiori is used in SAP ERP 6.0, configure successor apps
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | User Training | During conversion project | Conditional | train users on new Fiori apps
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Business Decision | Before conversion project | Mandatory | In SAP S/4HANA, the Foreign Trade (SD-FT) functionality is not available anymore. Instead, SAP S/4HANA for international trade within SAP S/4HANA is the successor.
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Customizing / Configuration | Before conversion project | Mandatory
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Customizing / Configuration | During conversion project | Mandatory | To migrate financial documents in Foreign Trade to Trade Finance, you carry out the migration steps available as Customizing activities (transaction SPRO, SAP Reference IMG) under: Conversion of Accounting to SAP S/4HANA-->Preparations and Migration of Customizing-->Preparations for Migration of Financial Documents to Trade Finance Conversion of Accounting to SAP S/4HANA-->Data Migration-->Migration of Financial Documents to Trade Finance Complete Migration of Financial Documents to Trade Finance conversion of Accounting to SAP S/4HANA-->Activities after Migration-->Manual Activities for Trade Finance"
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Data cleanup / archiving | During conversion project | Mandatory | You should Run as post conversion activity, report ZUPDATE_MARC_FOREIGN_TRADE(note 2458666) - to delete the content of the obsolete fileds. This avoids accidental side effects.
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Implementation project required | Before conversion project | Mandatory | GTS functionality is considerred as a pre-project, plan time and resources for the new implementation.
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Interface Adaption | Before conversion project | Mandatory
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Process Design / Blueprint | Before conversion project | Conditional | In case relevant SAP GTS needs to be installed, analysis of all foreign trade processes that are currently in use is requiered, before conversion.
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | User Training | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Business Decision | Before conversion project | Optional
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data cleanup / archiving | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data correction | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data migration | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Fiori Implementation | During conversion project | Optional
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Implementation project required | Before conversion project | Optional
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Process Design / Blueprint | Before conversion project | Optional
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Process Design / Blueprint | During conversion project | Mandatory
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | User Training | During conversion project | Mandatory
S4TWL - Generic Check for SAP S/4HANA Conversion and Upgrade (SI22: GENERIC_CHECKS) | Custom Code Adaption | Before or during conversion project | Mandatory | This simplification Item serves as an anchor for assigning custom code check related content, which is not related to any specific functional or technical area (e.g. deletion of unused orphaned objects).
S4TWL - Generic Check for SAP S/4HANA Conversion and Upgrade (SI22: GENERIC_CHECKS) | Miscellaneous | Before or during conversion project | Mandatory | This simplification item provides various generic, technical checks which need to run before a conversion or upgrade in SAP S/4HANA and which affect all customers - irrespective of the specific SAP S/4HANA target release.
S4TWL - Globalization – Financials (SI1_GSFIN) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Globalization – Financials (SI1_GSFIN) | Interface Adaption | During conversion project | Mandatory
S4TWL - Globalization – Financials (SI1_GSFIN) | User Training | During conversion project | Mandatory
S4TWL - Globalization – Logistics (SI1_GSLOG) | Custom Code Adaption | During conversion project | Optional
S4TWL - Globalization – Logistics (SI1_GSLOG) | Process Design / Blueprint | Before or during conversion project | Mandatory | SAP recommends using the following: •SAP Tax Declaration Framework for Fiscal and Accounting Legal Reporting. •TAXBRA tax procedure for the tax calculation. Note: SAP Tax Declaration Framework is part of the Compatible Add-ons and requires an additional license.
S4TWL - Globalization – Logistics (SI1_GSLOG) | User Training | During conversion project | Mandatory
S4TWL - Goods movements without exclusive locking by material valuation (SI7: Logistics_MM-IM) | Business Decision | Before conversion project | Mandatory
S4TWL - Goods movements without exclusive locking by material valuation (SI7: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Conditional | Set up locking method
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Business Operations | During conversion project | Mandatory | Execute report BTCTRNS2 of SNOTE 2499529
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Software Upgrade / Maintenance | During conversion project | Optional | Implement SAP Notes to prevent automatic execution of new job scheduling.
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Software Upgrade / Maintenance | During conversion project | Optional | Implement SAP Notes to prevent automatic execution of new job scheduling.
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Technical System Configuration | During conversion project | Optional | Decide if new job scheduling shall be used and adjust parameterization
S4TWL - LEGACY SYSTEM MIGRATION WORKBENCH (SI9: CT_LSMW) | Business Decision | Before conversion project | Optional | The use of LSMW is restricted for migrations to SAP S/4HANA. The use of LSMW for data load to SAP S/4HANA is not recommended and at the customer's own risk. SAP recommends using SAP S/4HANA Migration Cockpit and Migration Object Modeler instead of LSMW.
S4TWL - LEGACY SYSTEM MIGRATION WORKBENCH (SI9: CT_LSMW) | Interface Adaption | During conversion project | Conditional | If you still plan to use LSMW, provide customer specific adjustments or workarounds for restrictions on certain Batch Input or Direct Input programs.
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Custom Code Adaption | During or after conversion project | Optional
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Customizing / Configuration | Before or after conversion project | Mandatory | SAP S/4HANA Self-Service Procurement must be used instead of the SAP SRM MDM catalog.
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Data migration | During or after conversion project | Conditional | Set up a business user for SAP S/4HANA Self-Service Procurement.
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Interface Adaption | Before or after conversion project | Conditional | Content needs to be imported into S/4HANA via OCI5
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Process Design / Blueprint | Before conversion project | Mandatory | The SAP SRM catalog MDM is not available in SAP S/4HANA. It's replaced by the catalog search function as part of SAP S/4HANA Self-Service Procurement.
S4TWL - MDM Catalog (SI7: PROC_MDM ) | User Training | After conversion project | Optional
S4TWL - MRP in HANA (SI11: Logistics_PP) | Business Decision | Before or after conversion project | Optional | MRP Live is going to replace the classic MRP, which is not considered as future technology and therefore will be replaced in the future. You can start using MRP Live at any time, but you should make yourself familiar with details in the section "Business Process related information" in SAP Note 2268085 and MRP Live limitations in SAP Note 1914010.
S4TWL - MRP in HANA (SI11: Logistics_PP) | Custom Code Adaption | Before or after conversion project | Conditional | If your custom code reads data from the tables that are populated by the classic MRP, then it has to be adjusted to the use of MRP live as per SAP Note 2268085. Depending on when you start using MRP live it can be done before or after conversion
S4TWL - MRP in HANA (SI11: Logistics_PP) | Process Design / Blueprint | Before or after conversion project | Conditional | If you decide to use MRP live, then re-implement BAdI implementations and extensions of the classic MRP as AMDP BAdIs as per SAP Note 2268085
S4TWL - MRP in HANA (SI11: Logistics_PP) | User Training | Before conversion project | Conditional | If you decide to use MRP live, train the users on changes
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Business Operations | During conversion project | Mandatory
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Data correction | During conversion project | Mandatory
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Data migration | During conversion project | Mandatory
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | User Training | During or after conversion project | Optional
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory | Custom Code related information See SAP Note: 2215424, 2215852
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Data migration | During conversion project | Mandatory | ALE change pointer entries related to master data distribution (see SAP Help: LINK) have to be processed completely before the conversion to SAP S/4HANA. Changes recorded before the conversion will no longer be available compatibly after the conversion to SAP S/4HANA.
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Data migration | During conversion project | Conditional | The Long Material Number within the DIMP Add-On (Discrete Industries & Mill Products) Although the industry solution DIMP is part of SAP S/4HANA, the already existing DIMP LAMA-functionality for a long material number (LAMA) will not be part of SAP S/4HANA. In S/4HANA the material number is natively extended to 40 characters. Special conversion steps are needed to migrate the existing DIMP LAMA solution to the new S/4HANA extended material number. For further information on the conversion of the DIMP LAMA-functionality and the DIMP Manufacturer Parts Number to S/4HANA please check notes 2270396 and 2270836.
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Miscellaneous | Before conversion project | Optional | Conversion Pre-Checks related to Material Number Field Length Extension It´s recommended to execute conversion pre-check (for details see SAP Note: 2216958). For the conversion of selection variants see SAP Note 1696821 for details. Note that code adaptions will be needed even if you decide not to activate the extended material number functionality and stay with 18 characters
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Process Design / Blueprint | Before or during conversion project | Mandatory | The default setting, both after the conversion to SAP S/4HANA and for new installations, is that the extended material number functionality is NOT activated. To use a material number with 40 characters, you need to activate this functionality as described in SAP note 2267140 .
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | User Training | During conversion project | Optional | Use of new Material Number Field Length
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Business Decision | Before or during conversion project | Optional | Deactivation of the statistical moving average is not mandatory in SAP S/4HANA, but is nevertheless recommended in order to achieve a significant increase of transactional data throughput for goods movements. It is important to note that the deactivation is not reversible.
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Conditional | The report SAPRCKM_NO_EXCLUSIVELY_LOCKING can be used to deactivate the statistical moving average price.
S4TWL - New advanced ATP in SAP S/4HANA – Table VBBS (SI1: Logistics_ATP) | Custom Code Adaption | During conversion project | Mandatory | If you have custom code calling table VBBS, create a db view on table VBBE, and use that view instead of the table VBBS. SAP Note: 2209696
S4TWL - New advanced ATP in SAP S/4HANA – Table VBBS (SI1: Logistics_ATP) | Data migration | During conversion project | Mandatory | Manual step only for SAP S/4HANA 1511 and SAP S/4HANA 1610, For SAP S/4HANA 1709 and newer, the necessary actions are automated and executed in SUM phase using identifying name ATP_XPRA_SUITE_TO_S4_V2. SAP Note: 2209696
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Business Decision | Before conversion project | Optional | Decide if new output management or NAST-based output shall be used.
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Custom Code Adaption | During conversion project | Conditional | Replace custom code for previous NAST based output management
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Customizing / Configuration | During conversion project | Conditional | Configure new output management.
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Landscape Redesign | After conversion project | Conditional | If new output management is used, setup required technical infrastructure
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Process Design / Blueprint | During or after conversion project | Conditional | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated.
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Technical System Configuration | After conversion project | Conditional | Configure technical infrastructure for new output management
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | User Training | After conversion project | Optional
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Business Decision | Before conversion project | Mandatory | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated.
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Custom Code Adaption | During conversion project | Conditional | Replace custom code for previous NAST-based output management.
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Customizing / Configuration | During conversion project | Conditional | Configure new output management.
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Landscape Redesign | After conversion project | Conditional | If new output management is used, setup required technical infrastructure
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Process Design / Blueprint | During or after conversion project | Conditional | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated.
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Technical System Configuration | After conversion project | Conditional | Configure technical infrastructure for new output management
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | User Training | After conversion project | Optional
S4TWL - Planning File (SI12: Logistics_PP) | Custom Code Adaption | During conversion project | Conditional | If exist, related custom code has to be adjusted. See SAP Note 2227059
S4TWL - Planning File (SI12: Logistics_PP) | Data migration | During conversion project | Mandatory | After the system conversion, you should run report PPH_SETUP_MRPRECORDS to populate the new planning file table with operative MRP records (PP-MRP) and the report PPH_SETUP_MRPRECORDS_SIMU for simulative MRP records (PP-MP-LTP). Alternatively, you can also use the conversion reports PPH_CONVERT_MRPRECORDS and PPH_CONVERT_MRPRECORDS_SIMU.
S4TWL - Planning Horizon (SI35: Logistics_PP) | Custom Code Adaption | During conversion project | Conditional | Customers can build their own planning application using the BAPI BAPI_MATERIAL_PLANNING. The BAPI has got the same planning parameter options as the classical planning transactions. In that context the processing key NETPL cannot be used any more.
S4TWL - Planning Horizon (SI35: Logistics_PP) | Data cleanup / archiving | During conversion project | Mandatory | If there are still variants for the planning run batch Transactions having the processing key filled with NETPL, these variants have to be deleted.
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Data migration | After conversion project | Mandatory
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Technical System Configuration | During conversion project | Mandatory
S4TWL - Profitability Analysis (SI9: FIN_CO) | Business Decision | Before conversion project | Optional
S4TWL - Profitability Analysis (SI9: FIN_CO) | Customizing / Configuration | During conversion project | Mandatory
S4TWL - Profitability Analysis (SI9: FIN_CO) | Implementation project required | Before conversion project | Optional
S4TWL - Profitability Analysis (SI9: FIN_CO) | User Training | During or after conversion project | Optional
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | Custom Code Adaption | During conversion project | Mandatory | Adjust or replace custom code refering to obsolete transactions
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | Customizing / Configuration | During conversion project | Optional | For certain replacements conifguratios need to be done
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | User Training | During conversion project | Mandatory
S4TWL - SAP HANA LIVE REPORTING (SI4_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory | If the customer copied calc views delivered by SAP or created user-defined calc views, check and remove if required
S4TWL - SAP HANA LIVE REPORTING (SI4_FIN_GL) | New developments | During conversion project | Mandatory | rebuild all existing reporting scenarios with CDS Views
S4TWL - SD Simplified Data Models (SI1: SD_GENERAL) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Side Panel functionality in SAP S/4HANA (on-premise) (SI14: CT_SIDE_PANELS) | Fiori Implementation | During or after conversion project | Optional | if obsolete side-panel CHIPS were used, consider Fiori apps as replacement
S4TWL - Side Panel functionality in SAP S/4HANA (on-premise) (SI14: CT_SIDE_PANELS) | User Training | During or after conversion project | Optional | train users on new Fiori apps
S4TWL - Simplification of copy/reference handling (SI5: MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory
S4TWL - Simplification of copy/reference handling (SI5: MasterData_PM) | Data migration | During conversion project | Mandatory
S4TWL - Simplified Product Master Tables Related to OMSR Transaction (SI3: MasterData_PM) | Customizing / Configuration | During conversion project | Conditional | Configuration necessary, if field selection settings within SAP name space exists
S4TWL - Specification Workbench Adjustments (SI14: Logistics_PSS) | User Training | Before or during conversion project | Optional
S4TWL - Summarization Hierarchies in Controlling (SI11: FIN_CO) | User Training | During conversion project | Mandatory
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Business Decision | Before conversion project | Mandatory | Supplier Invoice Archiving does not fully support ILM Integration (with upgade to 1809 ILM Integration is fully supported)
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Data correction | During conversion project | Mandatory | Implement new BAdIs as indicated in SAP Note 2578291.
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Process Design / Blueprint | Before or during conversion project | Mandatory | Adapt the process due to changes in functionality
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Business Decision | Before conversion project | Mandatory | The functionalities SAP Internet Sales, SAP E-Commerce, SAP Web Channel, and SAP Web Channel Experience Management in SD are not supported in SAP S/4HANA and have been replaced by SAP Commerce in SAP S/4HANA 1610.
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Custom Code Adaption | Before or during conversion project | Conditional | Remove the usages of SAP objects in customer objects for which the custom code check refers to note 2225107 as they will not work anymore
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Process Design / Blueprint | Before or during conversion project | Mandatory | See SAP Note 2271161 for the list of unavailable transactions and functionalities. Replacement functionality is SAP Commerce in SAP S/4HANA 1610.
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | User Training | Before or during conversion project | Mandatory
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | Custom Code Adaption | During conversion project | Mandatory
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | Interface Adaption | During conversion project | Mandatory
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | User Training | During conversion project | Optional